## Slide 1
ONE DELIVERY MANAGEMENT SYSTEM · ODMS
Delivery Governance &
Weekly Status Reporting
A practical guide for Project Managers — how to report, what good looks like, and the guardrails that keep delivery on track.
FBSC · Filinvest Business Solutions Corp.

## Slide 2
WHY IT MATTERS
What ODMS gives a Project Manager
1
One source of truth
Every project's health, milestones, risks and budget in one place — no scattered trackers or slide decks.
2
A weekly rhythm
A single, predictable cadence: file once a week, and the portfolio view updates itself.
3
RAG visibility
Your status rolls up to Green / Amber / Red the moment you submit — leadership sees the same picture you do.
4
Governance built in
Reports route for approval, compliance is tracked, and stakeholders get an automatic weekly summary.

## Slide 3
WHO DOES WHAT
Roles around the report (you are the PM)
PM
Project Manager
Files the weekly status report for each project
Sets the six health indicators & comments
Keeps milestones, risks and budget current
Acts on 'changes requested', re-submits
Requests project completion when done
Reviewer / Approver
Delivery Lead or PMO — approves or requests changes on submitted reports.
Executive Leadership
Reads the portfolio dashboard; joins the delivery governance meeting.
Portfolio Lead / TBP
Oversight of the projects they sponsor or partner on.
Administrator
Sets up business units, employees, templates and access.

## Slide 4
THE RHYTHM
The weekly delivery-governance cadence
1
File the report
PM submits the weekly status report — by the cutoff, for the reporting week.
›
2
Review & approve
Reviewer approves or requests changes; the report's status settles from the workflow.
›
3
Roll-up & notify
Dashboards update; a themed status email goes to stakeholders.
›
4
Govern
Amber / Red and non-compliant projects are taken to the governance meeting.
Default reporting week = the PREVIOUS (last completed) week. Closed weeks can't be back-filled — file the current one.

## Slide 5
THE REPORT
Anatomy of a weekly status report
1
Executive Summary
A few sentences: where the project stands this week, in plain language.
2
Health Indicators (RAG)
Six areas rated Green / Amber / Red — the heart of the report.
3
Milestones
Progress against the plan; status per milestone (from the tracker).
4
Risks & Issues
The live register — what could hurt delivery, and what already has.
5
Budget & Schedule metrics
Actuals vs. plan — the numbers behind Budget and Schedule health.
6
Accomplishments / Next Steps
What was done this week and what happens next.

## Slide 6
HEALTH INDICATORS
The six RAG areas — and the golden rules
Scope
Schedule
Budget
Quality
Risks
Issues
TWO RULES YOU CAN'T SKIP
Overall Health is DERIVED from the six indicators — fix the indicators, don't fudge the headline.
Any indicator that is NOT Green requires a comment explaining why (and what you're doing about it).

## Slide 7
GUARDRAILS
What Green, Amber and Red actually mean
GREEN
On track
Scope, time & cost as planned
No help needed
Keep it honest — green isn't a default
AMBER
Needs monitoring
A concern that could become a problem
You have a plan, but flag it
Say what moves it back to green
RED
Needs action
Off track — impact is real now
Escalate; you need a decision or help
Never leave red without a comment

## Slide 8
MILESTONES
Milestones every delivery should carry
01
Project Kickoff / Initiation
02
Requirements / BU Sign-off
03
Design / Solution Approval
04
Build / Development Complete
05
UAT / Testing Complete
06
Go-Live / Deployment
07
Post-Go-Live Review / Closure
Make them count
Meaningful & verifiable — a clear 'done'
Dated: start and target end
Owned by someone accountable
Track outcomes, not every task
Go-Live is the one everyone watches

## Slide 9
GUARDRAILS
Populating milestones — do it right
STATUS VALUES
Not Started
In Progress
Completed
Seeded from the tracker
Each report starts from the project's milestone tracker — its latest dates & status. Edit what changed.
Completed = locked
Marking a milestone Completed locks it. Only tick it when it's genuinely, verifiably done.
Keep dates honest
Slipped a date? Move the target and turn Schedule Amber/Red with a comment — don't leave the old date.
At least one milestone
A report needs milestones. An empty plan is a red flag in itself.
Don't back-fill history
You report the current week; closed weeks show what was true then and can't be edited.

## Slide 10
REGISTER
Risks & Issues — keep the register alive
Type
Risk (might happen) or Issue (already happening).
Severity
High / Medium / Low — drives attention & the Top Risks widget.
Status
Open / In Progress / Closed.
Owner
A named person accountable — never blank.
Notes / mitigation
What you're doing about it.
GUARDRAILS
Raise risks EARLY — a surprise in Red is a governance failure.
Give every item an owner and a next action.
Close what's resolved — don't let the list grow a tail.
A live High risk should show up in the RAG.
Codes (R-/I-) are assigned for you — focus on the substance, not the numbering.

## Slide 11
THE NUMBERS
Budget & Schedule metrics
BAC
Budget at Completion
The approved budget — your baseline.
AC
Actual Spend
What's been spent to date.
% Comp
Percent Complete
Physical progress of the work.
EAC
Estimate at Completion
Forecast total cost at today's run-rate.
Var
Budget / Schedule Variance
Plan vs. actual — the story behind the RAG.
Fcst
Forecast Finish
When it will really land vs. baseline.
Enter actuals honestly — they feed Budget & Schedule health and the executive view. The app computes the variances.

## Slide 12
WORKFLOW
Submit → Review → (Complete)
Submit
Report goes to Pending Review and routes to the approver(s).
Approved
All approvers sign off — the week is done and rolls up as Approved.
Changes Requested
Sent back with remarks — fix and re-submit (it re-enters the queue).
COMPLETING A PROJECT
When every milestone is Completed, submitting offers “Submit for Completion” — this REQUESTS completion, it doesn't close the project.
The approver then sees Decline / Approve. Approve (on final sign-off) marks the project Completed; Decline sends it back.

## Slide 13
VISIBILITY
Compliance & the executive view
Completed / Submitted
Pending Review
Not Submitted
Compliance tracks whether every due project reported this cycle. “Not Submitted” is visible to leadership — don't be on it.
WHAT THE EXECUTIVE DASHBOARD SHOWS
Portfolio RAG (Active / Green / Amber / Red)
Projects by BU & Health by category
Projects requiring executive attention
Weekly reporting compliance
Top risks this week
Upcoming milestones (next 5 days)

## Slide 14
QUICK REFERENCE
PM guardrails — do's & don'ts
DO
File every week, on time
Rate RAG honestly — amber early beats red late
Comment on every non-Green indicator
Keep milestones, dates & risks current
Give every risk an owner and next step
Raise issues before they surprise anyone
DON'T
Skip a week or back-fill closed ones
Leave Amber / Red without a comment
Mark milestones done prematurely (they lock)
Fudge the overall health headline
Let closed risks linger on the register
File empty accomplishments / next steps

## Slide 15
The habit that keeps delivery honest
Report weekly. Rate honestly. Keep the plan and register current. Ask for help in amber, not red.
1 report
per project, every week
6 areas
RAG, with comments when not green
1 truth
your report is what leadership sees
One Delivery Management System · ODMS