## User Matrix
Role | Project | Project Status Report | Approval Page
Project Manager | Add, Edit, View | Add, Edit, View
Executive Leadership | View | View
Delivery/Portfolio Lead | Add, Edit, View | Edit, View | Approve
PMO Admin | Add, Edit, View | View

## Metrics
Budget Metrics
Metric | Definition | Typical Calculation | Business Rules
Budget at Completion (BAC) | Total authorized budget for completing the project. | Approved project budget | Initially derived from the approved budget when project is added in the project register, maybe overwritten in case of approved change requests.
Actual Cost (AC) | Total cost incurred as of the reporting date, including labor, vendors, licenses, infrastructure, and other expenses. | Sum of actual project expenditures | Computed offline and inputed in the tool.
% Actual Completion | Percentage of work completed as of the reporting period |  | Manual input by PM
Budget Utilization % | Percentage of the approved budget already spent. | Actual Cost ÷ Approved Budget × 100 | Computed.
Planned Value (PV) | Budgeted cost of the work that should have been completed by the reporting date. | Approved budget allocated to scheduled work | Computed offline and inputed in the tool.
Earned Value (EV) | Budgeted value of the work actually completed. | % Actual Completion × BAC | Computed, add a field for PM to indicate the % completion
Cost Variance (CV) | Indicates whether completed work is over or under budget. Positive is favorable. | EV − AC | Computed
Cost Performance Index (CPI) | Measures cost efficiency. A value below 1.00 means the project is spending more than planned for the work completed. | EV ÷ AC | Computed
Estimate at Completion (EAC) | Forecast of the project’s total cost at completion. | Actuals to date + forecast | Computed offline and inputed in the tool.
Estimate to Complete (ETC) | Additional amount expected to be spent to complete the remaining work. | EAC − AC | Computed
Variance at Completion (VAC) | Expected final budget surplus or overrun. Positive is favorable. | BAC − EAC | Computed
Schedule Metrics
Metric | Definition | Typical Calculation | Business Rules
Baseline Start Dates | Original approved dates against which schedule performance is measured. | Approved project baseline | Initially derive from the dates when project is created, maybe overwritten in case of change request, or new dates approved by business
Baseline Finish Dates | Original approved dates against which schedule performance is measured. | Approved project baseline | Initially derive from the dates when project is created, maybe overwritten in case of change request, or new dates approved by business
Forecast Finish Date | Current expected completion date based on actual progress and remaining work. | Latest project schedule forecast | Manually inputed by PM
Schedule Variance in Days | Number of calendar or working days the project is ahead of or behind the baseline. | Forecast Finish − Baseline Finish | Computed
Schedule Variance (SV) | Earned-value measure showing whether the completed work is ahead of or behind plan. Positive is favorable. | EV − PV | Computed
Schedule Performance Index (SPI) | Measures schedule efficiency. Below 1.00 indicates that less work has been completed than planned. | EV ÷ PV | Computed