## Status Report
Project ID | Reporting Week | Year | Submission Date | Executive Summary | Actual Spend | Budget at Completion | % Actual Completion | Planned Value | Estimate at Completion | Forecast Finish Date | Accomplishments | Next Steps | Scope Status | Scope Comment | Schedule Status | Schedule Comment | Budget Status | Budget Comment | Quality Status | Quality Comment | Risks Status | Risks Comment | Issues Status | Issues Comment
A-FLI-00001 | 30 | 2026 | 7/24/2026 | Weekly status update - refer to accomplishments and next steps. | [6 empty] | On hold due to Unified Inventory View CR. Code is on top of Unified Inventory view | Decision from MAV or we will do Plan B | Red | Scope needs attention - placeholder comment; replace with the real note. | Red | Schedule needs attention - placeholder comment; replace with the real note. | Red | Budget needs attention - placeholder comment; replace with the real note. | Red | Quality needs attention - placeholder comment; replace with the real note. | Red | Risks needs attention - placeholder comment; replace with the real note. | Red | Issues needs attention - placeholder comment; replace with the real note.
A-FDC-00001 | 30 | 2026 | 7/24/2026 | Weekly status update - refer to accomplishments and next steps. | [6 empty] | realigning the E2E process flow to include additional scenarios | finalize the workflow and get approval from Ms. Chiqui and Sir Ven | Amber | Upcoming change request | Green | timeline to be updated once final workflow and scope are finalized | Green | update in budget due to CR | Green | Quality on track | Green | Updating project due to change ins cope | Green | No issues
A-FDC-00002 | 30 | 2026 | 7/24/2026 | Weekly status update - refer to accomplishments and next steps. | [6 empty] | - Shared the updated training materials to DG Working Group for targeted training - Shared the final training materials for the management orientation deck and included scenario in relation to the EDL Dashboard - Sent the invite for Management Orientation Training and Targeted Training (1st session) - Completed data domains: CWSI, PSHC, and PPMI/PWSI, FDC, FHC, SPI/DPI | - Finalize the training materials for the BU-targeted workshop - Send the invite for the Targeted Training (2nd and 3rd session), and Lesson Learnt Workshop - Completion of data domains and data roles for FLI, and FAI - Finalize the roles and names for EDO | Green | On track, preparing for rollout | Green | On track, preparing for rollout | Green | Internal OneTech project | Green | Quality on track | Amber | Potential risk due to delayed identification of data roles for FAI and FLI. | Green | No issues
A-FDC-00003 | 30 | 2026 | 7/24/2026 | Weekly status update - refer to accomplishments and next steps. | [8 empty] | Green |  | Green |  | Green |  | Green |  | Green |  | Green
A-HR-CoE-00001 | 30 | 2026 | 7/24/2026 | Weekly status update - refer to accomplishments and next steps. | [6 empty] | Pending decision for Executive Payroll project: - Will Execs do clock in or clock out? Or their timelogs is defaulted to present unless a leave was filed. - Decision on the proposed support will seat with HR and not with OneTech like the current support for Regular employees. | Secure approval on the proposed support. Data Migration | Green |  | Red | August target no longer feasible | Green | Seat charge | Red | Not started | Red | The proposed support, will require removal of access to production DB, Service speed related to access Prod DB might be affected. | Red | Issues needs attention - placeholder comment; replace with the real note.
A-HR-CoE-00002 | 30 | 2026 | 7/24/2026 | Weekly status update - refer to accomplishments and next steps. | [6 empty] | Ongoing development at completion rate 55% | Continue development | Green |  | Green | On Track | Green | Seat charge | Green | No major bugs | Green | No identified risks | Green | No identified issues
A-HR-CoE-00003 | 30 | 2026 | 7/24/2026 | Weekly status update - refer to accomplishments and next steps. | [6 empty] | Build Ongoing and now at 95% Ongoing testing | Testing and Demo to Business unit | Green |  | Green | On track | Green | Seat charge | Green | No major bugs | Green | No identified risks | Green | No identified issues
A-HR-CoE-00004 | 30 | 2026 | 7/24/2026 | Weekly status update - refer to accomplishments and next steps. | [6 empty] | Uploaded users in Cornerstone, Assigned roles, Created Pre-Go Live test cases and for review with HR team and Cornerstone. Planned rollout schedule: Coursera: July 2026 Cornerstone LMS: August 2026 | Review of Test cases with Cornerstone team | Green |  | Green | On track | Green | Seat charge | Green | No major bugs | Green | No identified risks | Green | No identified issues
A-FLI-00002 | 30 | 2026 | 7/24/2026 | Weekly status update - refer to accomplishments and next steps. | [6 empty] | Deployed to PROD July 22 | Stabilization period | Green |  | Green |  | Green |  | Green |  | Green |  | Green
A-FLI-00003 | 30 | 2026 | 7/24/2026 | Weekly status update - refer to accomplishments and next steps. | [6 empty] | Deployed Phase 1 - Phase 2 for mobilisation | For Mobilisation on Phase 2 | Green | For Mobilisation | Green | On track | Green |  | Amber | New QA feedback from daily meetings | Green | NO identified risks | Green | No identified issues
A-FLI-00004 | 30 | 2026 | 7/24/2026 | Weekly status update - refer to accomplishments and next steps. | [6 empty] | On hold due to Unified Inventory View CR. Code is on top of Unified Inventory view | Decision from MAV or we will do Plan B | Red | Scope needs attention - placeholder comment; replace with the real note. | Red | Schedule needs attention - placeholder comment; replace with the real note. | Amber | Budget needs attention - placeholder comment; replace with the real note. | Green |  | Red | Risks needs attention - placeholder comment; replace with the real note. | Red | Issues needs attention - placeholder comment; replace with the real note.
A-FLI-00005 | 30 | 2026 | 7/24/2026 | Weekly status update - refer to accomplishments and next steps. | [6 empty] | New CR items from BU. IA is not yet signed | Waiting for MAV and FAI decision | Red | Scope needs attention - placeholder comment; replace with the real note. | Red | Schedule needs attention - placeholder comment; replace with the real note. | Amber | Budget needs attention - placeholder comment; replace with the real note. | Green |  | Red | Risks needs attention - placeholder comment; replace with the real note. | Red | Issues needs attention - placeholder comment; replace with the real note.
A-FLI-00006 | 30 | 2026 | 7/24/2026 | Weekly status update - refer to accomplishments and next steps. | [8 empty] | Green |  | Green |  | Green |  | Green |  | Green |  | Green
A-HR-CoE-00005 | 30 | 2026 | 7/24/2026 | Weekly status update - refer to accomplishments and next steps. | [6 empty] | Received Process flow from Olga, HR. | Discussion with Olga regarding exit interview trigger | Green | Upcoming discovery discussions | Green |  | Green | Seat charge | Green | Not started | Green | No identified risks | Green | No identified issues
A-HR-CoE-00006 | 30 | 2026 | 7/24/2026 | Weekly status update - refer to accomplishments and next steps. | [6 empty] | Tested the workaround provided by Ramco in the TESTING environment this is now for payroll confirmation for the reflected amount. Completed Testing, pending confirmation from Payroll. Ms. Diana's team |  | Amber | Scope needs attention - placeholder comment; replace with the real note. | Green |  | Green | Seat charge | Amber | Not started | Green | No identified risks | Green | No identified issues
A-FDC-00004 | 30 | 2026 | 7/24/2026 | Weekly status update - refer to accomplishments and next steps. | [8 empty] | Amber | Scope needs attention - placeholder comment; replace with the real note. | Amber | Schedule needs attention - placeholder comment; replace with the real note. | Amber | Budget needs attention - placeholder comment; replace with the real note. | Amber | Quality needs attention - placeholder comment; replace with the real note. | Amber | Risks needs attention - placeholder comment; replace with the real note. | Amber | Issues needs attention - placeholder comment; replace with the real note.
A-SPI-00001 | 30 | 2026 | 7/24/2026 | Weekly status update - refer to accomplishments and next steps. | [6 empty] | Official Kick-off: July 28 | Official Kick-off | Green | For Team Mobilisation | Green |  | Green | This will be covered by FDC | Green | Official Kic-off Scheduled | Green | No identified risks | Green | No identified issues
A-FLI-00007 | 30 | 2026 | 7/24/2026 | Weekly status update - refer to accomplishments and next steps. | [8 empty] | Green |  | Green |  | Green |  | Green |  | Green |  | Green
A-SPI-00002 | 30 | 2026 | 7/24/2026 | Weekly status update - refer to accomplishments and next steps. | [6 empty] | Alignment with Kim (SPI) on 7/28 - Business rules to be provided on 2nd week of August 2026 | In parallel, BRD to be reviewed and signed-off by BU. No development mobilization yet | Green | Business process/rules documentation in progress | Green | On track | Green | No identified issues | Green |  | Green | No identified issues | Green | No identified issues
A-SPI-00003 | 30 | 2026 | 7/24/2026 | Weekly status update - refer to accomplishments and next steps. | [6 empty] | Waiting completion on functional testing by SPI | Expected presentation/update from SPI by 1st week of August 2026 | Green | Currently evaluating 5 vendors | Green | On track | Green | No identified issues | Green |  | Green | No identified issues | Green | No identified issues
A-FLI-00008 | 30 | 2026 | 7/24/2026 | Weekly status update - refer to accomplishments and next steps. | [6 empty] | On hold due to Unified Inventory View CR. Code is on top of Unified Inventory view | Decision from MAV or we will do Plan B | Red | Scope needs attention - placeholder comment; replace with the real note. | Red | Schedule needs attention - placeholder comment; replace with the real note. | Red | Budget needs attention - placeholder comment; replace with the real note. | Red | Quality needs attention - placeholder comment; replace with the real note. | Red | Risks needs attention - placeholder comment; replace with the real note. | Red | Issues needs attention - placeholder comment; replace with the real note.
A-FAI-00001 | 30 | 2026 | 7/24/2026 | Weekly status update - refer to accomplishments and next steps. | [8 empty] | Green |  | Green |  | Green |  | Green |  | Green |  | Green
A-FBSC-SS-00001 | 30 | 2026 | 7/24/2026 | Weekly status update - refer to accomplishments and next steps. | [6 empty] | Huawei IP Phone power adapter model and type forwarded to Zaraeya Roxas for purchase ¦ Local assignments identified for Collections, Billing, AP, Treasury, Cashier, Finance, Corporate Admin | Confirm IVR local number owners and complete front desk phone adapter purchase ¦ Finalize local number ownership and escalation path | Green | Scope on track | Amber | Awaiting confirmation from Nhelly Canetes on team member assignments | Green | Budget on track | Green | Quality on track | Amber | Delay in confirming assigned team members may impact go-live readiness | Green | No active issues
A-FBSC-SS-00002 | 30 | 2026 | 7/24/2026 | Weekly status update - refer to accomplishments and next steps. | [6 empty] | Backing support installed ¦ Solutioning continues on security concerns | Ensure QMS vendor proposal signoff ¦ Prepare BU Heads for August 11 ITSC presentation (9:00 AM - 11:00 AM) | Green | Scope on track | Amber | 65" TV delivery and vendor relocation of temporary 55" display still pending | Green | Budget on track | Green | Quality on track | Amber | Pending vendor proposal signoff and open security items may delay ITSC approval | Green | Vendor proposal pending signoff with Ms. Jed as of July 3
A-FBSC-SS-00003 | 30 | 2026 | 7/24/2026 | Weekly status update - refer to accomplishments and next steps. | [6 empty] | Vendor PM Wilfredo Iglesias scheduled onsite July 17, 2026 ¦ Several items already procured (digital signage TVs, 100" TV, ceiling drop poles, wireless presentation dongles, JBL speakers, boardroom/training room audio accessories) | Validate AV delivery status after July 17 onsite update ¦ Resolve any surplus/cancellation concerns ¦ Obtain cafeteria speaker quotation | Amber | Equipment already procured may limit scope changes or cancellation flexibility | Green | On track pending delivery confirmation | Amber | Several items already procured and can no longer be cancelled | Green | Quality on track | Amber | Equipment already procured may limit scope changes or cancellation flexibility | Green | Cafeteria speaker quotation remains pending
A-FBSC-SS-00004 | 30 | 2026 | 7/24/2026 | Weekly status update - refer to accomplishments and next steps. | [6 empty] | SSO and RBAC completed as of June 17, 2026 ¦ Security review ongoing ¦ MSA drafting ongoing | Resolve RMS security review findings (high/medium findings) ¦ Align governance ownership model ¦ Close high/medium findings before proceeding further | Green | Scope on track | Amber | Security review and governance discussions ongoing | Green | Budget on track | Green | Quality on track | Amber | Security findings and governance ownership remain unresolved | Amber | Open governance discussions on shared services ownership, governance coordination, and technical/business partnership model
A-FBSC-SS-00005 | 30 | 2026 | 7/24/2026 | Weekly status update - refer to accomplishments and next steps. | [6 empty] | Awaiting BU signoff for rollout ¦ SSO and RBAC completed | Secure BU approval from Gerald as advised by Patrick ¦ Proceed with rollout planning after approval | Green | Scope defined and ready for rollout | Amber | Rollout cannot proceed without BU signoff | Green | Budget on track | Green | Quality on track | Amber | Rollout cannot proceed without BU signoff | Green | No active issues
A-FBSC-SS-00006 | 30 | 2026 | 7/24/2026 | Weekly status update - refer to accomplishments and next steps. | [6 empty] | Presentation of Mock-up to ITG team has been completed. | Presentation of Mock-up to ITG team has been completed. Next step: ITG to seek approval from Carlo to replicate/configure the proposed setup within a sandbox environment for testing purposes. TBP to present cost to BU | Green | Scope on track | Amber | SOW delay may affect July 22 BU presentation and rollout schedule | Green | Budget on track | Green | Quality on track | Amber | Pending SOW signoff may delay rollout | Green | No active issues

## Milestones
Project ID | Reporting Week | Year | Milestone | Target Date | Status
A-FBSC-SS-00005 | 30 | 2026 | BU Signoff for Rollout | 7/31/2026 | In Progress
A-FBSC-SS-00005 | 30 | 2026 | ITSC Approval | 8/15/2026 | Not Started
A-FBSC-SS-00005 | 30 | 2026 | Rollout Planning | 8/31/2026 | Not Started
A-FBSC-SS-00006 | 30 | 2026 | Vendor Mock-up Creation | 7/21/2026 | Completed
A-FBSC-SS-00006 | 30 | 2026 | Live BU Presentation | 7/22/2026 | Completed
A-FBSC-SS-00006 | 30 | 2026 | SOW Signoff | 7/21/2026 | In Progress
A-FBSC-SS-00001 | 30 | 2026 | Team Member Assignment Confirmation | 7/31/2026 | In Progress
A-FBSC-SS-00001 | 30 | 2026 | Local Number Ownership Finalization | 7/31/2026 | In Progress
A-FBSC-SS-00001 | 30 | 2026 | Huawei IP Phone Adapter Purchase | 7/31/2026 | In Progress
A-FBSC-SS-00002 | 30 | 2026 | Backing Support Installation | 7/10/2026 | Completed
A-FBSC-SS-00002 | 30 | 2026 | 65" TV Delivery and Installation | 8/1/2026 | In Progress
A-FBSC-SS-00002 | 30 | 2026 | Vendor Proposal Signoff | 7/31/2026 | In Progress
A-FBSC-SS-00002 | 30 | 2026 | ITSC Presentation | 8/11/2026 | Not Started
A-FBSC-SS-00003 | 30 | 2026 | Vendor PM Onsite Visit | 7/17/2026 | Completed
A-FBSC-SS-00003 | 30 | 2026 | Equipment Delivery and Installation | 8/15/2026 | In Progress
A-FBSC-SS-00003 | 30 | 2026 | Cafeteria Speaker Quotation | 7/31/2026 | Completed
A-FBSC-SS-00004 | 30 | 2026 | SSO and RBAC Implementation | 6/17/2026 | Completed
A-FBSC-SS-00004 | 30 | 2026 | Security Review | 8/15/2026 | In Progress
A-FBSC-SS-00004 | 30 | 2026 | MSA Drafting | 8/15/2026 | In Progress
A-FBSC-SS-00004 | 30 | 2026 | Governance Ownership Alignment | 8/31/2026 | In Progress
A-FDC-00002 | 30 | 2026 | Idenification of data domains and data roles | 8/8/2026 | In Progress
A-FDC-00002 | 30 | 2026 | Management Orientation Training | 8/6/2026 | Not Started
A-FDC-00002 | 30 | 2026 | Targeted Training | 9/17/2026 | Not Started
A-FDC-00002 | 30 | 2026 | Lesson Learn Training | 10/22/2026 | Not Started
A-HR-CoE-00001 | 30 | 2026 | Data Migration | 8/10/2026 | Not Started
A-FLI-00001 | 30 | 2026 | TBD - placeholder milestone | 12/18/2026 | In Progress
A-FDC-00001 | 30 | 2026 | TBD - placeholder milestone | 12/18/2026 | In Progress
A-FDC-00003 | 30 | 2026 | TBD - placeholder milestone | 12/18/2026 | In Progress
A-HR-CoE-00002 | 30 | 2026 | TBD - placeholder milestone | 12/18/2026 | In Progress
A-HR-CoE-00003 | 30 | 2026 | TBD - placeholder milestone | 12/18/2026 | In Progress
A-HR-CoE-00004 | 30 | 2026 | TBD - placeholder milestone | 12/18/2026 | In Progress
A-FLI-00002 | 30 | 2026 | TBD - placeholder milestone | 12/18/2026 | In Progress
A-FLI-00003 | 30 | 2026 | TBD - placeholder milestone | 12/18/2026 | In Progress
A-FLI-00004 | 30 | 2026 | TBD - placeholder milestone | 12/18/2026 | In Progress
A-FLI-00005 | 30 | 2026 | TBD - placeholder milestone | 12/18/2026 | In Progress
A-FLI-00006 | 30 | 2026 | TBD - placeholder milestone | 12/18/2026 | In Progress
A-HR-CoE-00005 | 30 | 2026 | TBD - placeholder milestone | 12/18/2026 | In Progress
A-HR-CoE-00006 | 30 | 2026 | TBD - placeholder milestone | 12/18/2026 | In Progress
A-FDC-00004 | 30 | 2026 | TBD - placeholder milestone | 12/18/2026 | In Progress
A-SPI-00001 | 30 | 2026 | TBD - placeholder milestone | 12/18/2026 | In Progress
A-FLI-00007 | 30 | 2026 | TBD - placeholder milestone | 12/18/2026 | In Progress
A-SPI-00002 | 30 | 2026 | TBD - placeholder milestone | 12/18/2026 | In Progress
A-SPI-00003 | 30 | 2026 | TBD - placeholder milestone | 12/18/2026 | In Progress
A-FLI-00008 | 30 | 2026 | TBD - placeholder milestone | 12/18/2026 | In Progress
A-FAI-00001 | 30 | 2026 | TBD - placeholder milestone | 12/18/2026 | In Progress

## Risks & Issues
Project ID | Reporting Week | Year | Type | Title | Severity | Status | Owner | Date Raised | Notes
A-FBSC-SS-00005 | 30 | 2026 | Risk | Rollout Delay Due to Pending BU Signoff | High | Open | Lowie Macasinag Sevilla | 7/17/2026 | Rollout cannot proceed without BU signoff. Secure approval from ITSC as advised by Ms Vhie.
A-FBSC-SS-00006 | 30 | 2026 | Risk | SOW Delay Affecting BU Presentation | High | Open | Lowie Macasinag Sevilla | 7/17/2026 | SOW delay may affect July 22 BU presentation and rollout schedule. Prioritize SOW review and business validation of mock-up.
A-FBSC-SS-00001 | 30 | 2026 | Risk | Go-Live Readiness Impact from Team Assignment Delay | Medium | Open | Lowie Macasinag Sevilla | 7/17/2026 | Delay in confirming assigned team members may impact go-live readiness. Finalize local number ownership and escalation path.
A-FBSC-SS-00001 | 30 | 2026 | Issue | Pending Team Member Assignments | Medium | Open | Lowie Macasinag Sevilla | 7/17/2026 | Awaiting confirmation from Nhelly Canetes on team members for Collections (4994), Billing (4995), AP (4996), Treasury/Cashier (4997), Finance (4998), Corporate Admin (4993).
A-FBSC-SS-00002 | 30 | 2026 | Risk | ITSC Approval Delay | High | Open | Lowie Macasinag Sevilla | 7/17/2026 | Pending vendor proposal signoff and open security items may delay ITSC approval. Close proposal signoff and prepare BU Heads for ITSC attendance on August 11.
A-FBSC-SS-00002 | 30 | 2026 | Issue | Vendor Proposal Pending Signoff | Medium | Open | Lowie Macasinag Sevilla | 7/3/2026 | Vendor proposal pending signoff with Ms. Jed as of July 3. Security concerns solutioning ongoing.
A-FBSC-SS-00002 | 30 | 2026 | Issue | 65" TV Delivery Pending | Low | Open | Lowie Macasinag Sevilla | 7/17/2026 | 65" TV delivery and vendor relocation of temporary 55" display still pending.
A-FBSC-SS-00003 | 30 | 2026 | Risk | Limited Flexibility for Scope Changes | Medium | Open | Lowie Macasinag Sevilla | 7/17/2026 | Equipment already procured may limit scope changes or cancellation flexibility. Confirm final installation scope, surplus handling, and pending cafeteria speaker quotation.
A-FBSC-SS-00003 | 30 | 2026 | Issue | Cafeteria Speaker Quotation Pending | Low | Open | Lowie Macasinag Sevilla | 7/17/2026 | Cafeteria speaker quotation remains pending. Several items already procured and cannot be cancelled.
A-FBSC-SS-00004 | 30 | 2026 | Risk | Unresolved Security Findings | High | Open | Lowie Macasinag Sevilla | 7/17/2026 | Security findings and governance ownership remain unresolved. Align ownership model and close high/medium findings before proceeding further.
A-FBSC-SS-00004 | 30 | 2026 | Issue | Governance Ownership Discussions Open | Medium | Open | Lowie Macasinag Sevilla | 6/17/2026 | Open governance discussions include shared services ownership, governance coordination, and technical/business partnership model required to sustain the platform.